## Client Release Summary
School | STC
Final tag details | https://scm.virtusa.com/schoolmanagemen/tags/akura-QA-2.11.0.6/
New Features | Term Mark Import/ Export Term Mark sheet can be Imported and Exported (with or without marks) Staff Leave application and Approval Staff member leave application and approval has been refactored to provide complete online leave application and approval facility Class Wise Student Term Mark Sheet Report This report has been modified to provide more details to the user.
Known Issues | 1. When the user add/edit/delete any qualification of a existing staff member system does not display any confirmation message. 2. When adding new system users, system allow to add an acadamic system user with non-acadamic registration number and non-acadamic user with a acadamic registration number 3. When the user genarate the Staff Profile Report with educational details (for the staff member who has educational details successfully entered in the system) system will randomly display 'null' for the Educational Details of a particular user. 4. Manage Sports Categories – Sports categories with dependencies (already assigned to students) can be eidtied. 5. When the user tries to complete the Term Mark Entry by selecting the checkbox, without entering marks to all the fields, following incorrect error message is displyed. 'Mark Entry has been already completed, blank values are not allowed.' instead of 'Blank values are not allowed' (This message is given only in Chrome and IE8, no message given in Firefox) 6. When user tries to apply a leave, at the save if the user cancels it, user should be able to edit the leave dates as he wants. But system does not allow user to select dates beyond "Date To" field previously seleted date. 7. Staff-class teacher allocation- When user trying to do a new class teacher allocation soon after deleting an already available allocation (for any teacher) system navigates to an error page. 8. Reporting – Grade Wise Best Student Attendance Report - When user selects to generate the report by selecting 'All' for Grades for a particular year, system displays validation message as "Please fill the mandatory field(s) marked with an asterisk (*)" 9. Co-Curriculars - If user add a external activity with invalid values (special characters) for the mandatory fields, system saves the record successfully while giving the correct error message. 10. In Student summary report date of birth and address of student gets overlapped 11. Manage System Users - Mandatory field validation message contains additional unnecessary symbols. 12. Student Progress Summary - It display a default rank for the students who's term marks are not completed 13. In Student summary report some table headers are getting repeated. 14. Class wise student report - Student numbering (No: column values)is repeating for each page 15. If user perform an advance search, page scroll downs to end of the page 16. Some of the reports are not generated in IE8 17. Bulk_Upload - System randomly navigates to an error page while uploading Subjects 18. Term Mark Import -The number of successfully imported records shown in the summary file is always equal to the number of students in the class, irrespetive of actual number of success records. 19. When the user save the Student atendans by checking the Confirm Attendance check box, system saves the atendance while clearing the checked check box 20. When the user try to upload a Staff atendance file, the system navigates to an error page 21. When Per Day Staff Category Wise Attendance Report is generated, the system navigates to an error page 22. Search functionality is not working properly in User management 23. When the user clicks the generate report button of the Student attendance on special event report without provide any mandatory field values, System navigates to an error page. 24. If a correct sibling parent record and an incorrect sibling parent record is available in the same excel file, both records move to erroneous file. 25. If two siblings parent records exist in the same excel file being uploaded, parent information are saved only for the first sibling. Therefore it has to be done in two different instances. 26. Uploading a file by deleting some content results in generation of erroneous record file with blank records. 27. Parent Details page, Student Details page and Staff Details page can be scrolled out of the theme in Chrome.
QA Status | Testing Completed
Tested Browsers | Firefox 25 – (Fully Tested) - Recommended Browser
Chrome 31
IE 8
Note | Recommended Adobe Reader version 11.0
Known Issues
Defect distribution described below
Open Defects
ID | Description | Explanation | Severity | Priority
DEF2342 | Staff – Qualifications – Not displaying any Confirmation message for 'Add', 'Edit' and 'Delete' functions. | When the user add/edit/delete any qualification of a existing staff member system does not display any confirmation message.
DEF2350 | Manage System Users - Add New System User – system allow to add a new teacher user with non-academic registration number and clerical user with academic registration number | When adding new system users, system allow to add an acadamic system user with non-acadamic registration number and non-acadamic user with a acadamic registration number
DEF2353 | Reporting – Staff General Reports – Staff Profile Report – When generating the report for a Present staff member who is having educational qualification, randomly it displays "null" for the Education | When the user genarate the Staff Profile Report with educational details (for the staff member who has educational details successfully entered in the system) system will randomly display 'null' for the Educational Details of a particular user.
DEF2216 | Reference – Manage Sports Categories – Can edit a sport category which is has already assigned to a student. | Manage Sports Categories – Sports categories with dependencies (already assigned to students) can be eidtied.
DEF2344 | Student mark entry : System generates wrong validation message | when the user tries to complete the Term Mark Entry by selecting the checkbox, without entering marks to all the fields, following incorrect error message is displyed. 'Mark Entry has been already completed, blank values are not allowed.' instead of 'Blank values are not allowed' (This message is given only in Chrome and IE8, no message given in FF)
DEF2261 | Description : Leave apply- after cancelling a leave request (by staff member) user is prohibited of selecting a start date beyond from the previously selected(cancelled leave request) date when applying for a leave again | When user tries to apply a leave, at the save if the user cancels it, user should be able to edit the leave dates as he wants. But system does not allow user to select dates beyond "Date To" field previously seleted date.
DEF2275 | Description: Staff-class teacher allocation- system navigate to error page when adding a new class teacher allocation after deleting an existing allocation | Staff-class teacher allocation- When user trying to do a new class teacher allocation soon after deleting an already available allocation (for any teacher) system navigates to an error page.
DEF2285 | Reporting – Grade Wise Best Student Attendance Report - System displays a validation message as "Please fill the mandatory field(s) marked with an asterisk (*)" | Reporting – Grade Wise Best Student Attendance Report - When user selects to generate the report by selecting 'All' for Grades for a particular year, system displays validation message as "Please fill the mandatory field(s) marked with an asterisk (*)"
DEF2288 | Co-Curriculars - System allow to save the External Activities/ Achievements with invalid characters | Co-Curriculars - If user add a external activity with invalid values (special characters) for the mandatory fields, system saves the record successfully while giving the correct error message.
DEF2296 | student summary report: student address and date of birth fields are having UI issue | In Student summary report date of birth and address of student gets overlapped
DEF2298 | Manage system user: Registration no/ admission no field disappear with generates error | Manage system user - If an error occurred when user tries to create a user login, the given "Registration No:" or "Admission No:" field gets diappeared.
DEF2310 | Manage System Users - Validation Message contains unnecessary symbols. | Manage System Users - Mandatory field validation message contains additional unnecessary symbols.
DEF2315 | Student Progress Summary - It display the rank for the students who's marks are not completed in the mark entry table | Student Progress Summary - It display a default rank for the students who's term marks are not completed
DEF2318 | existing school (db dump) Student General report- Student summary report- Student sub term marks evaluation table header repeated | In Student summary report some table headers are getting repeated. *Existing DB
DEF2326 | Class wise student report - "No:" column numbers are renewing from page to page. | Class wise student report - Student numbering (No: column values)is repeating for each page
DEF2184 | student search: page scroll way down to automatically | If user perform an advance search, page scroll downs to end of the page
DEF2186/ DEF1812 | Reporting – IE8 not supported for report generating. | Some of the reports are not generated in IE8
DEF2199 | Bulk_Upload - System directs to an error page while uploading Subjects | Bulk_Upload - System randomly navigates to an error page while uploading Subjects
DEF2204 | Import marks: The summery text file doesn't contain the correct count of the error records found. | Term Mark Import -The number of successfully imported records shown in the summary file is always equal to the number of students in the class, irrespetive of actual number of success records.
DEF2167 | System clears the "Confirm attendance" check box while saving. | When the user save the Student atendans by checking the Confirm Attendance check box, system saves the atendance while clearing the checked check box
DEF2168 | When an attendance file is uploaded, navigates to an error page. | When the user try to upload a Staff atendance file, the system navigates to an error page
DEF2363 | Reporting – Staff Attendance Reports – Per Day Staff Category Wise Attendance Report – When generating the report for absent type it navigates to the error page. | When Per Day Staff Category Wise Attendance Report is generated, the system navigates to an error page
DEF2364 | User management: It displays teacher and the parent users under search results | Search functionality is not working properly in User management
DEF2380 | Reporting: When the generate report button is clicked without provide any mandatory field values, System navigates to an error page. (Student attendance on special events) | When the user clicks the generate report button of the Student attendance on special event report without provide any mandatory field values, System navigates to an error page.
DEF2156 | Bulk Upload – Parent Upload – Uploading correct sibling parent record with incorrect sibling parent record moved both records to erroneous file | If a correct sibling parent record and an incorrect sibling parent record is available in the same excel file, both records move to erroneous file.
DEF2151 |  | If two siblings parent records exist in the same excel file being uploaded, parent information are saved only for the first sibling. Therefore it has to be done in two different instances.
DEF2133 |  | Uploading a file by deleting some content results in generation of erroneous record file with blank records.
DEF1798 |  | Parent Details page, Student Details page and Staff Details page can be scrolled out of the theme in Chrome.
Reopen Defects
ID | Description |  | Severity | Priority