## Release Plan
|  | Release | Iteration | ID | User Story | Estimated Size | Priority
|  | 1 - Interim Go Live | Sprint 1 | 1000 | Search for resumes by keywords | 3 | 1
|  |  |  | 1001 | Enter Resume online | 5 | 2
|  |  |  | 1002 | Post a job opening | 2 | 3
|  |  |  | 1008 | Add a social network | 3 | 4
|  |  |  | 1013 | Download resume in PDF format | 2 | 22
[5 empty] | Total | 15
|  |  | Sprint 2 | 1016 | Add a recruiter profile | 5 | 5
|  |  |  | 1017 | Add a rating to a recruiter | 8 | 6
|  |  |  | 1020 | Browse a recruiter profiles by location | 2 | 17
[5 empty] | Total | 15
|  |  | Sprint 3 | 1025 | Review skill suggestions | 13 | 7
|  |  |  | 1026 | Approve a skill suggession | 3 | 8
[5 empty] | Total | 16
[5 empty] | Total for the Release | 46
|  | 2 - Major Go Live | Sprint 4 | 1003 | Find a job opening that matches my skills | 3 | 9
|  |  |  | 1004 | Find resumes with skills that match a job openning | 5 | 10
|  |  |  | 1010 | Add alert for job positions on my social networks | 5 | 12
|  |  |  | 1015 | Preview my resume with different templates | 1 | 15 | 46
[5 empty] | Total | 14 |  | 56
|  |  | Sprint 5 | 1006 | Search job openning by loacation | 8 | 11
|  |  |  | 1007 | Filter job opennings by salary range | 5 | 21
|  |  |  | 1012 | Upload resume in word format | 3 | 14
[5 empty] | Total | 16
|  |  | Sprint 6 | 1011 | Filter job opennings by industry type | 13 | 13
[5 empty] | Total | 13
|  |  | Sprint 7 | 1018 | Browse recruiter profiles by rating | 5 | 16
|  |  |  | 1024 | Suggest a new skill | 8 | 19
[5 empty] | Total | 13
[5 empty] | Total for the Release | 56
Burn down Chart
Release | Sprint | Planned Velocity | Actual Velocity
1 | 1 | 15 | 10
| 2 | 15 | 8
| 3 | 15 | 20
2 | 4 | 15 | 15
| 5 | 15 | 15
| 6 | 15
| 7 | 15

## Sheet1
Burn down Chart
Release | Sprint | Planned Velocity | Planned Effort | Actual Velocity | Actual Effort
| 0 |  | 105 |  | 105
1 | 1 | 15 | 90 | 10 | 95
| 2 | 15 | 75 | 8 | 87
| 3 | 15 | 60 | 20 | 67
2 | 4 | 15 | 45 | 15 | 52
| 5 | 15 | 30 | 15 | 37
| 6 | 15 | 15
| 7 | 15 | 0
| Sprint | Planned Burndown | Actual Burndown
| 0 | 105 | 105
| 1 | 90 | 95
| 2 | 75 | 87
| 3 | 60 | 67
| 4 | 45 | 52
| 5 | 30 | 37
| 6 | 15
| 7 | 0