## Slide 1: Scrum in the Real World

## Slide 2: Scrum in the Real World
Starting Scrum Projects
Expressing Requirements with User Stories
Release Planning and Estimation
Release Tracking and Responding to Project Delays

## Slide 3
Time
Sprint 1
Sprint 2
Sprint 3
Sprint 4
Sprint 5
Sprint 6
Sprint 7
Sprint 8
Sprint 9
Sprint 10
Development Start
Release Date
Scrum Kickoff
ScrumMaster teaches Scrum to everyone and assign the Scrum roles
Product Owner communicates the vision and goals of the release
Product Owner leads the creation of the Product Backlog (with lots of input)
Team does the High-level size estimation of the Product Backlog
Product Owner does Initial prioritization of the Product Backlog (with lots of input)
Release Planning Meeting to estimate release date / budget
Team sets up their development and test environments
Team does the initial high-level design and architecture (just enough to get started)
Don’t forget - all of the above will evolve during project
Scrum
Kickoff
(brief)

## Slide 4: Agile Planning Onion

## Slide 6: Sample Product Roadmap

## Slide 7: Product Roadmap vs Product Backlog

## Slide 8: Elevator Pitch
An elevator pitch is a crisp message that communicates key features of the project in a succinct way so that others can easily understand it.
Imagine if your CEO asked about the project in the lift going up to your office. Can you communicate what the project is about before the elevator gets from the ground to the tenth floor?
Elevator Pitch
• Brings clarity and focus to project.
• Forces team to think about the customer.
• Forces hard decisions to be made:
• who is it for? how is it different?

## Slide 9: Elevator Pitch

## Slide 10: Defining Product from Customer Point of View

## Slide 11: Scrum in the Real World
Starting Scrum Projects
Expressing Requirements with User Stories
Release Planning and Estimation
Release Tracking and Responding to Project Delays

## Slide 12: Creating the Product Backlog
Product Backlog
8
9
10
11
12
7
1
2
3
4
5
6

## Slide 13: User Stories for Clarity
User stories are a widely used format for describing features on the Product Backlog
User Stories are short, plain-language descriptions of the feature, centered on the consumer of the feature, what they need it to do, and why
The 3 C’s: Card, Confirmation, Conversation

## Slide 14: The Card
15. Review Pending Requests. [Accessible from the Dashboard]. Enables user to view all their currently unapproved requests in the system. The page should display a table that lists each of the pending requests, the date of the request, the type of the request (vacation day, personal day, or sick day), and the first 30 characters of the “explanation field”.
As an employee,
I want to see all the requests I’ve submitted that are pending my manager’s approval
So that I can see which have been approved and which have not been approved

## Slide 15: The Confirmation – Back of Card
Acceptance Criteria
Notes
15. Review Pending Requests. [Accessible from the Dashboard]. Enables user to view all their currently unapproved requests in the system. The page should display a table that lists each of the pending requests, the date of the request, the type of the request (vacation day, personal day, or sick day), and the first 30 characters of the “explanation field”.
All pending requests are shown
Last 5 approved or denied requests are shown
Requests are shown in a table, in reverse chronological order
For each request, the date and type of request is shown, as well as the first 30 characters of the explanation
If no requests pending, “No requests pending” appears
For each request, show whether a reminder has been sent to the manager yet
Showing the last 5 approved or denied requests is not in the original specification, but it’s quick and easy to include

## Slide 16: The Conversation
The card only covers the most basic information
The next level of detail comes in conversations between the Product Owner and the Team
  Screen shots
  Items out of scope
  Process Flows
  Baseline Estimate (Mandatory)
  Data Migration
  Non-functional requirements

## Slide 18: Scrum in the Real World
Starting Scrum Projects
Expressing Requirements with User Stories
Release Planning and Estimation
Release Tracking and Responding to Project Delays

## Slide 19: What is Release Planning
How much will be done by August 30?
When can we ship with this set of features?
How much will it cost to get this set of features?

## Slide 20: Big Picture Implications
Helps predict revenue and budget models
Ensures departmental readiness
  Marketing
  Sales
  Training
  Support

## Slide 21: Release Planning
Product Owner responsibility
Driven typically by time but can be by scope
Velocity stability will increase release accuracy
Release planning should occur at end of every sprint:
  Scrum team and relevant stakeholders
  Discuss goals, risks, probable release dates
  Estimate any new PBIs
  Product Owner will adjust the Release Burndown and release plan

## Slide 22: Release Options
Release after multiple sprints
Release every sprint
Release every feature

## Slide 23
Who’s Involved In Release Planning?
Customers / Product Owners:
  define stories;
  set priorities; and
  put stories into iterations.
Developers:
  estimate stories;
  point out significant technical risks; and
  establish velocity, a measure of team development capacity.
© 2014 Intelliware Development Inc.
Notes: Ideally most of the defining, priorities and estimating has been done before Release Planning.
Velocity – estimating units per iteration
The significance of technical risks is that risky stories should be done earlier to mitigate potential issues

## Slide 24
Defining a Release Plan
Develop high level product backlog - the ‘what’ not the ‘how’
Estimate the size of the product backlog using relative estimation technique
Establish iteration lengths
  Iterations are generally 1 to 3 weeks long.
  Developers decide what will be in the iteration in collaboration with the customer / product owner.
  Smaller projects tend to have shorter iterations.
  Size is important as release dates are usually based on external constraints.
Determine the velocity
  Estimate of how many estimating units can be completed per iteration.
  Developer responsibility.
  Unit of measurement used does not matter – be it points, ideal days, or something else.
Organize stories into iterations
  Based on business and technical priorities.
© 2014 Intelliware Development Inc.
The process of deciding what goes into a release
Notes: Release dates are often based on external constraints and can’t be moved
Setting iteration lengths is not a hard science and is largely based on the team’s prior experiences and comfort level and the size of the project
It is important to remember that the Release Plan is not set in stone and will change from Iteration to Iteration as business priorities change

## Slide 25
Example of a Release Plan
© 2014 Intelliware Development Inc.
Iteration 1
Iteration 2
Release | Iteration | Stories | Size
Alpha | 1 | Home Page | 1
 |  | Login | 1
 |  | Display Account Summary List | 2
 |  | Display Account Details | 1
 |  | List Transaction Summary for an Account | 1
 |  | Add New Transaction | 2
 |  | Logout | 1
 |  | TOTAL | 9
 | 2 | Add New Account | 2
 |  | Deactivate and Remove Existing Account | 1
 |  | Modify Account Information | 1
 |  | Delete a Transaction | 1
 |  | Modify Transaction or Move to Different Account | 2
 |  | TOTAL | 7
Here’s an example of a
release that consists of 2
iterations with 12 stories.
.
Notes: You can use an application like Jira or Mingle that sorts the cards into iterations for you, or a simple table produced using Word or Excel also works – whatever tool you choose doesn’t matter

## Slide 26: Release backlog

## Slide 29: Feature Driven Release Planning
The sum of all features within in a release can be divided by the expected velocity. This will then result in the number of sprints needed to complete the requested functionality

## Slide 30: Date Driven Release Planning
Multiply the velocity by the number of Sprints and we'll get the total work that can be completed within the given timeline.

## Slide 31
Getting Started…

## Slide 32
Sprint 1
Sprint 2
Sprint 3
Sprint 4
Sprint 5
Sprint 6
January
February
March
120
points
Product backlog = 120 points

## Slide 33
Sprint 1
Sprint 2
Sprint 3
Sprint 4
Sprint 5
Sprint 6
January
February
March
120
points
Product backlog = 120 points
1+13+5
=
19

## Slide 34
Sprint 1
Sprint 2
Sprint 3
Sprint 4
Sprint 5
Sprint 6
January
February
March
120
points
5 + 8 + 5 + 2 +1
=
21
1+13+5
=
19
Avg velocity = 20 points
per sprint
Product backlog = 120 points
Velocity = 20 points
Forecast for completion = 6 sprints
Full backlog delivery

## Slide 35
Sprint 1
Sprint 2
Sprint 3
Sprint 4
Sprint 5
Sprint 6
January
February
March
140
points
21
19
Product backlog = 140 points
Velocity = 20 points
Forecast for completion = 7 sprints
Full backlog delivery
New Requirement
Sprint 7
Increased scope
T&M/ Fixed time ?

## Slide 36
Sprint 1
Sprint 2
Sprint 3
Sprint 4
Sprint 5
Sprint 6
January
February
March
100
points
21
19
Product backlog = 100 points
Velocity = 20 points
Forecast for completion = 5 sprints
Full backlog delivery
Decreased scope

## Slide 37
Sprint 1
Sprint 2
Sprint 3
Sprint 4
Sprint 5
Sprint 6
January
February
March
124
points
35
35
Product backlog = 124 points
Velocity = 35 points
Forecast for completion = 3.5 sprints
Full backlog delivery
Increased velocity

## Slide 38
Sprint 1
Sprint 2
Sprint 3
Sprint 4
Sprint 5
Sprint 6
January
February
March
124
points
Product backlog = 124 points
Velocity = 17 points
Forecast for completion = 7 sprints
16
18
Full backlog delivery
Sprint 7
Decreased velocity

## Slide 39
Sprint 1
Sprint 2
Sprint 3
Sprint 4
Sprint 5
Sprint 6
January
February
March
120
points
21
19
Product backlog = 120 points
Velocity = 20 points
Forecast for completion = 6 sprints
Full backlog delivery
Release 1
R1
Scheduling releases
Product backlog = 60 points
Velocity = 20 points
Forecast for completion = 3 sprints
(release)
60 points

## Slide 40: Enhanced Release Burndown
Work Remaining
Time
Original Release Date
March 7
Adjusted Release Date
April 11
Sprint 1
Sprint 2
Sprint 3
Project will
finish in this
range
Sprint 4
Sprint 5
Thanks to: Mike Cohn, Mountain Goat Software
240
120
0
60
180
60

## Slide 41: Enhanced Release Burndown
Work Remaining
Time
Original Release Date
March 7
Adjusted
Release
Date
March 1
Sprint 1
Sprint 2
Sprint 3
Project will
finish in this
range
Sprint 4
Sprint 5
Thanks to: Mike Cohn, Mountain Goat Software
240
120
0
60
180
60

## Slide 42
90
80
70
60
50
40
30
20
10
0
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Release Burndown Chart
Sprints
End Development
Release
2 extra Sprints needed to finish Release Backlog
Remove 13 points from Release Backlog to launch on time